## Slide 1
Activity
Milestones
2015
2015
Today
Day 1
5
9
13
17
21
25
29
33
37
Team Member List and Draft Problem Description
10/29/2015
Initial Mechanical Design Presentation (Task List, Criteria, Constraints)
11/3/2015
Pick-up LEGO NXT and Tetrix Kits
11/5/2015
Fomal Project Description with Freehand Sketches of Design
11/6/2015
Formal Design Report (Goals, Objectives, Evaluation of Designs, Project Planning)
11/16/2015
Software Design and Physical Mock-up Presentation
11/16/2015
Checklist for Objectives of the Robot
11/24/2015
Demonstration of Robot
11/24/2015
Final Report of Project (Analysis, Evaluation, Reflection)
12/4/2015
2 days
10/27/2015 - 10/28/2015
Problem statement
3 days
10/29/2015 - 11/2/2015
Tasks, Criteria, Constraints
3 days
11/3/2015 - 11/5/2015
Freehand sketches
2 days
11/4/2015 - 11/5/2015
Formal Project Description summarized
6 days
11/6/2015 - 11/15/2015
Build complete mechanical design
4 days
11/10/2015 - 11/15/2015
Complete design report
3 days
11/11/2015 - 11/15/2015
Flow chart of software design (functions)
0 days
11/14/2015 - 11/15/2015
Practice presentation of software design and mechanical design progress
5 days
11/16/2015 - 11/21/2015
Set actuators and sensors of the robot
2 days
11/19/2015 - 11/22/2015
Software creation, testing and debugging
0 days
11/22/2015
Robot objectives task list for demo day
2 days
11/22/2015 - 11/24/2015
Final testing and touch-ups
6 days
11/25/2015 - 12/2/2015
Complete final report